## Sheet1
Door Measurement ..SFPL..
Sr No | Tower | Flat No | Door Type | L/R | Width | Height | Wall Thickness | Beam Thickness | Wall Option | Beam Option | Remark | Width Op Diff | Height Op Diff | Corrected Wall Option | Corrected Beam Option | Corrected Width | Corrected Height | Corrected Thickness | Width Action | Height Action | Sub Frame Vertical Nos. | Sub Frame Top- Nos. | Sub Frame C/S | Received Frame Size For Prod. (45Âº JOINT) W | Received Frame Size For Prod. (45Âº JOINT) H | Received Frame Size For Prod. (45Âº JOINT) T | Inside A/C Design | Size of Inside (A/C) | C/S (Cx8) / (AxBx13) | Inside A/C Width | Inside A/C Height | Outside A/C Design | Size of Outside (A/C) | C/S (Cx8) / (AxBx13) | Outside A/C Width | Outside A/C Height | Frame Ext C/S (Dx15) | Frame Ext Width | Frame Ext Height | Leaf Width | Leaf Height | Leaf Thickness
1 |  | 1101 | MD01 | Left | 1085 | 2110 | 185 | 185 | 1 | 1 | NA | 35 | 10 | 1 | 1 | 1050 | 2100 | 185 | Correct Width to 1050 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 1030 | 2090 | 150 X 50 | Telescopic | 35 | 35 X 63 X 13 | 1070 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 1070 | 2110 | 0 X 0 | 0 | 0 | 958.5 | 2046 | 41.8
2 |  | 1102 | MD01 | Right | 1080 | 2110 | 170 | 170 | 2 | 2 | NA | 30 | 10 | 2 | 2 | 1050 | 2100 | 170 | Correct Width to 1050 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 1030 | 2090 | 150 X 50 | Telescopic | 35 | 35 X 48 X 13 | 1070 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 1070 | 2110 | 0 X 0 | 0 | 0 | 958.5 | 2046 | 41.8
3 |  | 1103 | MD01 | Left | 1100 | 2100 | 175 | 175 | 3 | 3 | NA | 50 | 0 | 3 | 3 | 1050 | 2100 | 170 | Correct Width to 1050 | All Ok | 1 | 1 | 170 X 12 | 1020 | 2080 | 150 X 50 | Telescopic | 35 | 35 X 48 X 13 | 1060 | 2105 | Telescopic | 35 | 35 X 28 X 13 | 1060 | 2100 | 0 X 0 | 0 | 0 | 948.5 | 2036 | 41.8
4 |  | 1104 | MD01 | Right | 1090 | 2110 | 175 | 175 | 4 | 4 | NA | 40 | 10 | 4 | 4 | 1050 | 2100 | 170 | Correct Width to 1050 | Correct Heigt to 2100 | 2 | 1 | 170 X 12 | 1010 | 2080 | 150 X 50 | Telescopic | 35 | 35 X 48 X 13 | 1050 | 2105 | Telescopic | 35 | 35 X 28 X 13 | 1050 | 2100 | 0 X 0 | 0 | 0 | 938.5 | 2036 | 41.8
5 |  | 1201 | MD01 | Left | 1080 | 2120 | 190 | 190 | 5 | 5 | NA | 30 | 20 | 5 | 5 | 1050 | 2100 | 185 | Correct Width to 1050 | Correct Heigt to 2100 | 2 | 1 | 185 X 12 | 1010 | 2080 | 150 X 50 | Telescopic | 35 | 35 X 63 X 13 | 1050 | 2105 | Telescopic | 35 | 35 X 28 X 13 | 1050 | 2100 | 0 X 0 | 0 | 0 | 938.5 | 2036 | 41.8
6 |  | 1202 | MD01 | Right | 1090 | 2110 | 175 | 175 | 6 | 1 | NA | 40 | 10 | 6 | 1 | 1050 | 2100 | 170 | Correct Width to 1050 | Correct Heigt to 2100 | 2 | 0 | 170 X 12 | 1010 | 2090 | 150 X 50 | Telescopic | 35 | 35 X 48 X 13 | 1050 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 1050 | 2110 | 0 X 0 | 0 | 0 | 938.5 | 2046 | 41.8
7 |  | 1203 | MD01 | Left | 1090 | 2110 | 175 | 175 | 7 | 1 | NA | 40 | 10 | 7 | 1 | 1050 | 2100 | 170 | Correct Width to 1050 | Correct Heigt to 2100 | 2 | 0 | 170 X 12 | 1010 | 2090 | 150 X 50 | Telescopic | 35 | 35 X 48 X 13 | 1050 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 1050 | 2110 | 0 X 0 | 0 | 0 | 938.5 | 2046 | 41.8
8 |  | 1204 | MD01 | Right | 1055 | 2130 | 180 | 180 | 3 | 1 | NA | 5 | 30 | 3 | 1 | 1050 | 2100 | 170 | Correct Width to 1050 | Correct Heigt to 2100 | 1 | 0 | 170 X 12 | 1020 | 2090 | 150 X 50 | Telescopic | 35 | 35 X 48 X 13 | 1060 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 1060 | 2110 | 0 X 0 | 0 | 0 | 948.5 | 2046 | 41.8
9 |  | 1301 | MD01 | Left | 1095 | 2110 | 200 | 200 | 3 | 1 | NA | 45 | 10 | 3 | 1 | 1050 | 2100 | 200 | Correct Width to 1050 | Correct Heigt to 2100 | 1 | 0 | 200 X 12 | 1020 | 2090 | 150 X 50 | Telescopic | 35 | 35 X 78 X 13 | 1060 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 1060 | 2110 | 0 X 0 | 0 | 0 | 948.5 | 2046 | 41.8
10 |  | 1302 | MD01 | Right | 1080 | 2105 | 185 | 185 | 3 | 1 | NA | 30 | 5 | 3 | 1 | 1050 | 2100 | 185 | Correct Width to 1050 | Correct Heigt to 2100 | 1 | 0 | 185 X 12 | 1020 | 2090 | 150 X 50 | Telescopic | 35 | 35 X 63 X 13 | 1060 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 1060 | 2110 | 0 X 0 | 0 | 0 | 948.5 | 2046 | 41.8
11 |  | 1303 | MD01 | Left | 1100 | 2100 | 175 | 175 | 1 | 1 | NA | 50 | 0 | 1 | 1 | 1050 | 2100 | 170 | Correct Width to 1050 | All Ok | 0 | 0 | 0 X 0 | 1030 | 2090 | 150 X 50 | Telescopic | 35 | 35 X 48 X 13 | 1070 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 1070 | 2110 | 0 X 0 | 0 | 0 | 958.5 | 2046 | 41.8
12 |  | 1304 | MD01 | Right | 1090 | 2120 | 175 | 175 | 3 | 1 | NA | 40 | 20 | 3 | 1 | 1050 | 2100 | 170 | Correct Width to 1050 | Correct Heigt to 2100 | 1 | 0 | 170 X 12 | 1020 | 2090 | 150 X 50 | Telescopic | 35 | 35 X 48 X 13 | 1060 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 1060 | 2110 | 0 X 0 | 0 | 0 | 948.5 | 2046 | 41.8
13 |  | 1101 | MD01 | Left | 1090 | 2100 | 195 | 195 | 3 | 1 | NA | 40 | 0 | 3 | 1 | 1050 | 2100 | 185 | Correct Width to 1050 | All Ok | 1 | 0 | 185 X 12 | 1020 | 2090 | 150 X 50 | Telescopic | 35 | 35 X 63 X 13 | 1060 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 1060 | 2110 | 0 X 0 | 0 | 0 | 948.5 | 2046 | 41.8
14 |  | 1102 | MD01 | Right | 1100 | 2100 | 190 | 190 | 3 | 1 | NA | 50 | 0 | 3 | 1 | 1050 | 2100 | 185 | Correct Width to 1050 | All Ok | 1 | 0 | 185 X 12 | 1020 | 2090 | 150 X 50 | Telescopic | 35 | 35 X 63 X 13 | 1060 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 1060 | 2110 | 0 X 0 | 0 | 0 | 948.5 | 2046 | 41.8
15 |  | 1103 | MD01 | Left | 1090 | 2110 | 175 | 175 | 1 | 1 | NA | 40 | 10 | 1 | 1 | 1050 | 2100 | 170 | Correct Width to 1050 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 1030 | 2090 | 150 X 50 | Telescopic | 35 | 35 X 48 X 13 | 1070 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 1070 | 2110 | 0 X 0 | 0 | 0 | 958.5 | 2046 | 41.8
16 |  | 1104 | MD01 | Right | 1090 | 2100 | 205 | 205 | 1 | 1 | NA | 40 | 0 | 1 | 1 | 1050 | 2100 | 200 | Correct Width to 1050 | All Ok | 0 | 0 | 0 X 0 | 1030 | 2090 | 150 X 50 | Telescopic | 35 | 35 X 78 X 13 | 1070 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 1070 | 2110 | 0 X 0 | 0 | 0 | 958.5 | 2046 | 41.8
17 |  | 1201 | MD01 | Left | 1085 | 2120 | 200 | 200 | 3 | 1 | NA | 35 | 20 | 3 | 1 | 1050 | 2100 | 200 | Correct Width to 1050 | Correct Heigt to 2100 | 1 | 0 | 200 X 12 | 1020 | 2090 | 150 X 50 | Telescopic | 35 | 35 X 78 X 13 | 1060 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 1060 | 2110 | 0 X 0 | 0 | 0 | 948.5 | 2046 | 41.8
18 |  | 1202 | MD01 | Right | 1110 | 2110 | 185 | 185 | 3 | 1 | NA | 60 | 10 | 3 | 1 | 1050 | 2100 | 185 | Correct Width to 1050 | Correct Heigt to 2100 | 1 | 0 | 185 X 12 | 1020 | 2090 | 150 X 50 | Telescopic | 35 | 35 X 63 X 13 | 1060 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 1060 | 2110 | 0 X 0 | 0 | 0 | 948.5 | 2046 | 41.8
19 |  | 1203 | MD01 | Left | 1100 | 2110 | 180 | 180 | 1 | 1 | NA | 50 | 10 | 1 | 1 | 1050 | 2100 | 170 | Correct Width to 1050 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 1030 | 2090 | 150 X 50 | Telescopic | 35 | 35 X 48 X 13 | 1070 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 1070 | 2110 | 0 X 0 | 0 | 0 | 958.5 | 2046 | 41.8
20 |  | 1204 | MD01 | Right | 1100 | 2100 | 185 | 185 | 1 | 1 | NA | 50 | 0 | 1 | 1 | 1050 | 2100 | 185 | Correct Width to 1050 | All Ok | 0 | 0 | 0 X 0 | 1030 | 2090 | 150 X 50 | Telescopic | 35 | 35 X 63 X 13 | 1070 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 1070 | 2110 | 0 X 0 | 0 | 0 | 958.5 | 2046 | 41.8
21 |  | 1301 | MD01 | Left | 1090 | 2120 | 190 | 190 | 3 | 1 | NA | 40 | 20 | 3 | 1 | 1050 | 2100 | 185 | Correct Width to 1050 | Correct Heigt to 2100 | 1 | 0 | 185 X 12 | 1020 | 2090 | 150 X 50 | Telescopic | 35 | 35 X 63 X 13 | 1060 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 1060 | 2110 | 0 X 0 | 0 | 0 | 948.5 | 2046 | 41.8
22 |  | 1302 | MD01 | Right | 1100 | 2115 | 180 | 180 | 3 | 1 | NA | 50 | 15 | 3 | 1 | 1050 | 2100 | 170 | Correct Width to 1050 | Correct Heigt to 2100 | 1 | 0 | 170 X 12 | 1020 | 2090 | 150 X 50 | Telescopic | 35 | 35 X 48 X 13 | 1060 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 1060 | 2110 | 0 X 0 | 0 | 0 | 948.5 | 2046 | 41.8
23 |  | 1303 | MD01 | Left | 1090 | 2110 | 190 | 190 | 1 | 1 | NA | 40 | 10 | 1 | 1 | 1050 | 2100 | 185 | Correct Width to 1050 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 1030 | 2090 | 150 X 50 | Telescopic | 35 | 35 X 63 X 13 | 1070 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 1070 | 2110 | 0 X 0 | 0 | 0 | 958.5 | 2046 | 41.8
24 |  | 1304 | MD01 | Right | 1100 | 2080 | 175 | 175 | 1 | 1 | NA | 50 | -20 | 1 | 1 | 1050 | 2100 | 170 | Correct Width to 1050 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 1030 | 2090 | 150 X 50 | Telescopic | 35 | 35 X 48 X 13 | 1070 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 1070 | 2110 | 0 X 0 | 0 | 0 | 958.5 | 2046 | 41.8
25 |  | 1101 | BD01 | Right | 985 | 2110 | 150 | 150 | 1 | 1 | NA | 35 | 10 | 1 | 1 | 950 | 2100 | 150 | Correct Width to 950 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 930 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 63 X 13 | 970 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 970 | 2110 | 0 X 0 | 0 | 0 | 858.5 | 2046 | 37.5
26 |  | 1101 | BD01 | Left | 960 | 2110 | 150 | 150 | 2 | 2 | NA | 10 | 10 | 2 | 2 | 950 | 2100 | 150 | Correct Width to 950 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 930 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 63 X 13 | 970 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 970 | 2110 | 0 X 0 | 0 | 0 | 858.5 | 2046 | 37.5
27 |  | 1101 | BD01 | Right | 955 | 2110 | 145 | 145 | 3 | 3 | NA | 5 | 10 | 3 | 3 | 950 | 2100 | 135 | Correct Width to 950 | Correct Heigt to 2100 | 1 | 1 | 135 X 12 | 920 | 2080 | 115 X 44 | Telescopic | 35 | 35 X 48 X 13 | 960 | 2105 | Telescopic | 35 | 35 X 28 X 13 | 960 | 2100 | 0 X 0 | 0 | 0 | 848.5 | 2036 | 37.5
28 |  | 1102 | BD01 | Left | 960 | 2110 | 150 | 150 | 4 | 4 | NA | 10 | 10 | 4 | 4 | 950 | 2100 | 150 | Correct Width to 950 | Correct Heigt to 2100 | 2 | 1 | 150 X 12 | 910 | 2080 | 115 X 44 | Telescopic | 35 | 35 X 63 X 13 | 950 | 2105 | Telescopic | 35 | 35 X 28 X 13 | 950 | 2100 | 0 X 0 | 0 | 0 | 838.5 | 2036 | 37.5
29 |  | 1102 | BD01 | Right | 935 | 2120 | 210 | 210 | 5 | 5 | NA | -15 | 20 | 5 | 5 | 950 | 2100 | 210 | Correct Width to 950 | Correct Heigt to 2100 | 2 | 1 | 210 X 12 | 910 | 2080 | 115 X 44 | Flat | 35 | 35 X 8 | 950 | 2105 | Telescopic | 35 | 35 X 28 X 13 | 950 | 2100 | 110 X 15 | 0 | 2085 | 838.5 | 2036 | 37.5
30 |  | 1103 | BD01 | Left | 950 | 2090 | 160 | 160 | 6 | 1 | NA | 0 | -10 | 6 | 1 | 950 | 2100 | 150 | All Ok | Correct Heigt to 2100 | 2 | 0 | 150 X 12 | 910 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 63 X 13 | 950 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 950 | 2110 | 0 X 0 | 0 | 0 | 838.5 | 2046 | 37.5
31 |  | 1103 | BD01 | Left | 945 | 2090 | 150 | 150 | 7 | 1 | NA | -5 | -10 | 7 | 1 | 950 | 2100 | 150 | Correct Width to 950 | Correct Heigt to 2100 | 2 | 0 | 150 X 12 | 910 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 63 X 13 | 950 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 950 | 2110 | 0 X 0 | 0 | 0 | 838.5 | 2046 | 37.5
32 |  | 1103 | BD01 | Left | 955 | 2080 | 155 | 155 | 2 | 1 | NA | 5 | -20 | 2 | 1 | 950 | 2100 | 150 | Correct Width to 950 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 930 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 63 X 13 | 970 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 970 | 2110 | 0 X 0 | 0 | 0 | 858.5 | 2046 | 37.5
33 |  | 1104 | BD01 | Left | 985 | 2110 | 145 | 145 | 4 | 1 | NA | 35 | 10 | 4 | 1 | 950 | 2100 | 135 | Correct Width to 950 | Correct Heigt to 2100 | 2 | 0 | 135 X 12 | 910 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 48 X 13 | 950 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 950 | 2110 | 0 X 0 | 0 | 0 | 838.5 | 2046 | 37.5
34 |  | 1104 | BD01 | Left | 955 | 2110 | 150 | 150 | 2 | 1 | NA | 5 | 10 | 2 | 1 | 950 | 2100 | 150 | Correct Width to 950 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 930 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 63 X 13 | 970 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 970 | 2110 | 0 X 0 | 0 | 0 | 858.5 | 2046 | 37.5
35 |  | 1104 | BD01 | Right | 935 | 2090 | 165 | 165 | 4 | 1 | NA | -15 | -10 | 4 | 1 | 950 | 2100 | 165 | Correct Width to 950 | Correct Heigt to 2100 | 2 | 0 | 165 X 12 | 910 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 78 X 13 | 950 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 950 | 2110 | 0 X 0 | 0 | 0 | 838.5 | 2046 | 37.5
36 |  | 1201 | BD01 | Right | 1000 | 2100 | 135 | 135 | 4 | 1 | NA | 50 | 0 | 4 | 1 | 950 | 2100 | 135 | Correct Width to 950 | All Ok | 2 | 0 | 135 X 12 | 910 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 48 X 13 | 950 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 950 | 2110 | 0 X 0 | 0 | 0 | 838.5 | 2046 | 37.5
37 |  | 1201 | BD01 | Left | 960 | 2110 | 135 | 135 | 4 | 1 | NA | 10 | 10 | 4 | 1 | 950 | 2100 | 135 | Correct Width to 950 | Correct Heigt to 2100 | 2 | 0 | 135 X 12 | 910 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 48 X 13 | 950 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 950 | 2110 | 0 X 0 | 0 | 0 | 838.5 | 2046 | 37.5
38 |  | 1201 | BD01 | Right | 955 | 2100 | 145 | 145 | 2 | 1 | NA | 5 | 0 | 2 | 1 | 950 | 2100 | 135 | Correct Width to 950 | All Ok | 0 | 0 | 0 X 0 | 930 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 48 X 13 | 970 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 970 | 2110 | 0 X 0 | 0 | 0 | 858.5 | 2046 | 37.5
39 |  | 1202 | BD01 | Left | 955 | 2095 | 145 | 145 | 2 | 1 | NA | 5 | -5 | 2 | 1 | 950 | 2100 | 135 | Correct Width to 950 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 930 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 48 X 13 | 970 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 970 | 2110 | 0 X 0 | 0 | 0 | 858.5 | 2046 | 37.5
40 |  | 1202 | BD01 | Right | 930 | 2100 | 210 | 210 | 3 | 1 | NA | -20 | 0 | 3 | 1 | 950 | 2100 | 210 | Correct Width to 950 | All Ok | 1 | 0 | 210 X 12 | 920 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 960 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 960 | 2110 | 110 X 15 | 0 | 2090 | 848.5 | 2046 | 37.5
41 |  | 1203 | BD01 | Left | 955 | 2085 | 145 | 145 | 3 | 1 | NA | 5 | -15 | 3 | 1 | 950 | 2100 | 135 | Correct Width to 950 | Correct Heigt to 2100 | 1 | 0 | 135 X 12 | 920 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 48 X 13 | 960 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 960 | 2110 | 0 X 0 | 0 | 0 | 848.5 | 2046 | 37.5
42 |  | 1203 | BD01 | Left | 950 | 2085 | 145 | 145 | 3 | 1 | NA | 0 | -15 | 3 | 1 | 950 | 2100 | 135 | All Ok | Correct Heigt to 2100 | 1 | 0 | 135 X 12 | 920 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 48 X 13 | 960 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 960 | 2110 | 0 X 0 | 0 | 0 | 848.5 | 2046 | 37.5
43 |  | 1203 | BD01 | Left | 950 | 2090 | 145 | 145 | 2 | 1 | NA | 0 | -10 | 2 | 1 | 950 | 2100 | 135 | All Ok | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 930 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 48 X 13 | 970 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 970 | 2110 | 0 X 0 | 0 | 0 | 858.5 | 2046 | 37.5
44 |  | 1204 | BD01 | Left | 995 | 2110 | 135 | 135 | 4 | 1 | NA | 45 | 10 | 4 | 1 | 950 | 2100 | 135 | Correct Width to 950 | Correct Heigt to 2100 | 2 | 0 | 135 X 12 | 910 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 48 X 13 | 950 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 950 | 2110 | 0 X 0 | 0 | 0 | 838.5 | 2046 | 37.5
45 |  | 1204 | BD01 | Right | 970 | 2110 | 140 | 140 | 4 | 1 | NA | 20 | 10 | 4 | 1 | 950 | 2100 | 135 | Correct Width to 950 | Correct Heigt to 2100 | 2 | 0 | 135 X 12 | 910 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 48 X 13 | 950 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 950 | 2110 | 0 X 0 | 0 | 0 | 838.5 | 2046 | 37.5
46 |  | 1204 | BD01 | Left | 960 | 2110 | 140 | 140 | 2 | 1 | NA | 10 | 10 | 2 | 1 | 950 | 2100 | 135 | Correct Width to 950 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 930 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 48 X 13 | 970 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 970 | 2110 | 0 X 0 | 0 | 0 | 858.5 | 2046 | 37.5
47 |  | 1301 | BD01 | Right | 1010 | 2100 | 150 | 150 | 4 | 1 | NA | 60 | 0 | 4 | 1 | 950 | 2100 | 150 | Correct Width to 950 | All Ok | 2 | 0 | 150 X 12 | 910 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 63 X 13 | 950 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 950 | 2110 | 0 X 0 | 0 | 0 | 838.5 | 2046 | 37.5
48 |  | 1301 | BD01 | Right | 940 | 2110 | 145 | 145 | 2 | 1 | NA | -10 | 10 | 2 | 1 | 950 | 2100 | 135 | Correct Width to 950 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 930 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 48 X 13 | 970 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 970 | 2110 | 0 X 0 | 0 | 0 | 858.5 | 2046 | 37.5
49 |  | 1301 | BD01 | Left | 950 | 2110 | 150 | 150 | 4 | 1 | NA | 0 | 10 | 4 | 1 | 950 | 2100 | 150 | All Ok | Correct Heigt to 2100 | 2 | 0 | 150 X 12 | 910 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 63 X 13 | 950 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 950 | 2110 | 0 X 0 | 0 | 0 | 838.5 | 2046 | 37.5
50 |  | 1302 | BD01 | Right | 945 | 2090 | 210 | 210 | 3 | 1 | NA | -5 | -10 | 3 | 1 | 950 | 2100 | 210 | Correct Width to 950 | Correct Heigt to 2100 | 1 | 0 | 210 X 12 | 920 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 960 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 960 | 2110 | 110 X 15 | 0 | 2090 | 848.5 | 2046 | 37.5
51 |  | 1302 | BD01 | Left | 950 | 2095 | 150 | 150 | 2 | 1 | NA | 0 | -5 | 2 | 1 | 950 | 2100 | 150 | All Ok | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 930 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 63 X 13 | 970 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 970 | 2110 | 0 X 0 | 0 | 0 | 858.5 | 2046 | 37.5
52 |  | 1303 | BD01 | Left | 950 | 2105 | 145 | 145 | 3 | 1 | NA | 0 | 5 | 3 | 1 | 950 | 2100 | 135 | All Ok | Correct Heigt to 2100 | 1 | 0 | 135 X 12 | 920 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 48 X 13 | 960 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 960 | 2110 | 0 X 0 | 0 | 0 | 848.5 | 2046 | 37.5
53 |  | 1303 | BD01 | Left | 950 | 2105 | 150 | 150 | 3 | 1 | NA | 0 | 5 | 3 | 1 | 950 | 2100 | 150 | All Ok | Correct Heigt to 2100 | 1 | 0 | 150 X 12 | 920 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 63 X 13 | 960 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 960 | 2110 | 0 X 0 | 0 | 0 | 848.5 | 2046 | 37.5
54 |  | 1303 | BD01 | Left | 950 | 2110 | 145 | 145 | 2 | 1 | NA | 0 | 10 | 2 | 1 | 950 | 2100 | 135 | All Ok | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 930 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 48 X 13 | 970 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 970 | 2110 | 0 X 0 | 0 | 0 | 858.5 | 2046 | 37.5
55 |  | 1304 | BD01 | Left | 955 | 2140 | 155 | 155 | 4 | 1 | NA | 5 | 40 | 4 | 1 | 950 | 2100 | 150 | Correct Width to 950 | Correct Heigt to 2100 | 2 | 0 | 150 X 12 | 910 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 63 X 13 | 950 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 950 | 2110 | 0 X 0 | 0 | 0 | 838.5 | 2046 | 37.5
56 |  | 1304 | BD01 | Left | 955 | 2140 | 155 | 155 | 2 | 1 | NA | 5 | 40 | 2 | 1 | 950 | 2100 | 150 | Correct Width to 950 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 930 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 63 X 13 | 970 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 970 | 2110 | 0 X 0 | 0 | 0 | 858.5 | 2046 | 37.5
57 |  | 1304 | BD01 | Right | 940 | 2120 | 170 | 170 | 4 | 1 | NA | -10 | 20 | 4 | 1 | 950 | 2100 | 165 | Correct Width to 950 | Correct Heigt to 2100 | 2 | 0 | 165 X 12 | 910 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 78 X 13 | 950 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 950 | 2110 | 0 X 0 | 0 | 0 | 838.5 | 2046 | 37.5
58 |  | 1101 | BD01 | Right | 1000 | 2110 | 150 | 150 | 4 | 1 | NA | 50 | 10 | 4 | 1 | 950 | 2100 | 150 | Correct Width to 950 | Correct Heigt to 2100 | 2 | 0 | 150 X 12 | 910 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 63 X 13 | 950 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 950 | 2110 | 0 X 0 | 0 | 0 | 838.5 | 2046 | 37.5
59 |  | 1101 | BD01 | Right | 955 | 2110 | 150 | 150 | 2 | 1 | NA | 5 | 10 | 2 | 1 | 950 | 2100 | 150 | Correct Width to 950 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 930 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 63 X 13 | 970 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 970 | 2110 | 0 X 0 | 0 | 0 | 858.5 | 2046 | 37.5
60 |  | 1101 | BD01 | Left | 940 | 2100 | 150 | 150 | 4 | 1 | NA | -10 | 0 | 4 | 1 | 950 | 2100 | 150 | Correct Width to 950 | All Ok | 2 | 0 | 150 X 12 | 910 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 63 X 13 | 950 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 950 | 2110 | 0 X 0 | 0 | 0 | 838.5 | 2046 | 37.5
61 |  | 1102 | BD01 | Left | 955 | 2085 | 145 | 145 | 2 | 1 | NA | 5 | -15 | 2 | 1 | 950 | 2100 | 135 | Correct Width to 950 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 930 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 48 X 13 | 970 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 970 | 2110 | 0 X 0 | 0 | 0 | 858.5 | 2046 | 37.5
62 |  | 1102 | BD01 | Right | 945 | 2085 | 210 | 210 | 3 | 1 | NA | -5 | -15 | 3 | 1 | 950 | 2100 | 210 | Correct Width to 950 | Correct Heigt to 2100 | 1 | 0 | 210 X 12 | 920 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 960 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 960 | 2110 | 110 X 15 | 0 | 2090 | 848.5 | 2046 | 37.5
63 |  | 1103 | BD01 | Left | 955 | 2100 | 155 | 155 | 2 | 1 | NA | 5 | 0 | 2 | 1 | 950 | 2100 | 150 | Correct Width to 950 | All Ok | 0 | 0 | 0 X 0 | 930 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 63 X 13 | 970 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 970 | 2110 | 0 X 0 | 0 | 0 | 858.5 | 2046 | 37.5
64 |  | 1103 | BD01 | Left | 950 | 2090 | 160 | 160 | 3 | 1 | NA | 0 | -10 | 3 | 1 | 950 | 2100 | 150 | All Ok | Correct Heigt to 2100 | 1 | 0 | 150 X 12 | 920 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 63 X 13 | 960 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 960 | 2110 | 0 X 0 | 0 | 0 | 848.5 | 2046 | 37.5
65 |  | 1103 | BD01 | Left | 940 | 2090 | 150 | 150 | 3 | 1 | NA | -10 | -10 | 3 | 1 | 950 | 2100 | 150 | Correct Width to 950 | Correct Heigt to 2100 | 1 | 0 | 150 X 12 | 920 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 63 X 13 | 960 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 960 | 2110 | 0 X 0 | 0 | 0 | 848.5 | 2046 | 37.5
66 |  | 1104 | BD01 | Right | 940 | 2085 | 205 | 205 | 3 | 1 | NA | -10 | -15 | 3 | 1 | 950 | 2100 | 195 | Correct Width to 950 | Correct Heigt to 2100 | 1 | 0 | 195 X 12 | 920 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 960 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 960 | 2110 | 95 X 15 | 0 | 2090 | 848.5 | 2046 | 37.5
67 |  | 1104 | BD01 | Left | 945 | 2090 | 145 | 145 | 2 | 1 | NA | -5 | -10 | 2 | 1 | 950 | 2100 | 135 | Correct Width to 950 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 930 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 48 X 13 | 970 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 970 | 2110 | 0 X 0 | 0 | 0 | 858.5 | 2046 | 37.5
68 |  | 1201 | BD01 | Right | 980 | 2120 | 135 | 135 | 4 | 1 | NA | 30 | 20 | 4 | 1 | 950 | 2100 | 135 | Correct Width to 950 | Correct Heigt to 2100 | 2 | 0 | 135 X 12 | 910 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 48 X 13 | 950 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 950 | 2110 | 0 X 0 | 0 | 0 | 838.5 | 2046 | 37.5
69 |  | 1201 | BD01 | Right | 955 | 2115 | 155 | 155 | 2 | 1 | NA | 5 | 15 | 2 | 1 | 950 | 2100 | 150 | Correct Width to 950 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 930 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 63 X 13 | 970 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 970 | 2110 | 0 X 0 | 0 | 0 | 858.5 | 2046 | 37.5
70 |  | 1201 | BD01 | Left | 940 | 2120 | 140 | 140 | 4 | 1 | NA | -10 | 20 | 4 | 1 | 950 | 2100 | 135 | Correct Width to 950 | Correct Heigt to 2100 | 2 | 0 | 135 X 12 | 910 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 48 X 13 | 950 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 950 | 2110 | 0 X 0 | 0 | 0 | 838.5 | 2046 | 37.5
71 |  | 1202 | BD01 | Left | 955 | 2090 | 145 | 145 | 2 | 1 | NA | 5 | -10 | 2 | 1 | 950 | 2100 | 135 | Correct Width to 950 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 930 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 48 X 13 | 970 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 970 | 2110 | 0 X 0 | 0 | 0 | 858.5 | 2046 | 37.5
72 |  | 1202 | BD01 | Right | 935 | 2080 | 210 | 210 | 3 | 1 | NA | -15 | -20 | 3 | 1 | 950 | 2100 | 210 | Correct Width to 950 | Correct Heigt to 2100 | 1 | 0 | 210 X 12 | 920 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 960 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 960 | 2110 | 110 X 15 | 0 | 2090 | 848.5 | 2046 | 37.5
73 |  | 1203 | BD01 | Left | 950 | 2075 | 165 | 165 | 3 | 1 | NA | 0 | -25 | 3 | 1 | 950 | 2100 | 165 | All Ok | Correct Heigt to 2100 | 1 | 0 | 165 X 12 | 920 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 78 X 13 | 960 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 960 | 2110 | 0 X 0 | 0 | 0 | 848.5 | 2046 | 37.5
74 |  | 1203 | BD01 | Left | 955 | 2080 | 150 | 150 | 2 | 1 | NA | 5 | -20 | 2 | 1 | 950 | 2100 | 150 | Correct Width to 950 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 930 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 63 X 13 | 970 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 970 | 2110 | 0 X 0 | 0 | 0 | 858.5 | 2046 | 37.5
75 |  | 1203 | BD01 | Left | 895 | 2075 | 150 | 150 | 3 | 1 | NA | -55 | -25 | 3 | 1 | 950 | 2100 | 150 | Correct Width to 950 | Correct Heigt to 2100 | 1 | 0 | 150 X 12 | 920 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 63 X 13 | 960 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 960 | 2110 | 0 X 0 | 0 | 0 | 848.5 | 2046 | 37.5
76 |  | 1204 | BD01 | Right | 945 | 2100 | 210 | 210 | 3 | 1 | NA | -5 | 0 | 3 | 1 | 950 | 2100 | 210 | Correct Width to 950 | All Ok | 1 | 0 | 210 X 12 | 920 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 960 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 960 | 2110 | 110 X 15 | 0 | 2090 | 848.5 | 2046 | 37.5
77 |  | 1204 | BD01 | Left | 955 | 2085 | 140 | 140 | 2 | 1 | NA | 5 | -15 | 2 | 1 | 950 | 2100 | 135 | Correct Width to 950 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 930 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 48 X 13 | 970 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 970 | 2110 | 0 X 0 | 0 | 0 | 858.5 | 2046 | 37.5
78 |  | 1301 | BD01 | Right | 990 | 2115 | 140 | 140 | 4 | 1 | NA | 40 | 15 | 4 | 1 | 950 | 2100 | 135 | Correct Width to 950 | Correct Heigt to 2100 | 2 | 0 | 135 X 12 | 910 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 48 X 13 | 950 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 950 | 2110 | 0 X 0 | 0 | 0 | 838.5 | 2046 | 37.5
79 |  | 1301 | BD01 | Left | 950 | 2110 | 155 | 155 | 4 | 1 | NA | 0 | 10 | 4 | 1 | 950 | 2100 | 150 | All Ok | Correct Heigt to 2100 | 2 | 0 | 150 X 12 | 910 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 63 X 13 | 950 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 950 | 2110 | 0 X 0 | 0 | 0 | 838.5 | 2046 | 37.5
80 |  | 1301 | BD01 | Right | 935 | 2110 | 160 | 160 | 2 | 1 | NA | -15 | 10 | 2 | 1 | 950 | 2100 | 150 | Correct Width to 950 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 930 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 63 X 13 | 970 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 970 | 2110 | 0 X 0 | 0 | 0 | 858.5 | 2046 | 37.5
81 |  | 1302 | BD01 | Left | 940 | 2110 | 155 | 155 | 2 | 1 | NA | -10 | 10 | 2 | 1 | 950 | 2100 | 150 | Correct Width to 950 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 930 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 63 X 13 | 970 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 970 | 2110 | 0 X 0 | 0 | 0 | 858.5 | 2046 | 37.5
82 |  | 1302 | BD01 | Right | 940 | 2095 | 210 | 210 | 3 | 1 | NA | -10 | -5 | 3 | 1 | 950 | 2100 | 210 | Correct Width to 950 | Correct Heigt to 2100 | 1 | 0 | 210 X 12 | 920 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 960 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 960 | 2110 | 110 X 15 | 0 | 2090 | 848.5 | 2046 | 37.5
83 |  | 1303 | BD01 | Left | 955 | 2100 | 165 | 165 | 2 | 1 | NA | 5 | 0 | 2 | 1 | 950 | 2100 | 165 | Correct Width to 950 | All Ok | 0 | 0 | 0 X 0 | 930 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 78 X 13 | 970 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 970 | 2110 | 0 X 0 | 0 | 0 | 858.5 | 2046 | 37.5
84 |  | 1303 | BD01 | Left | 940 | 2100 | 165 | 165 | 3 | 1 | NA | -10 | 0 | 3 | 1 | 950 | 2100 | 165 | Correct Width to 950 | All Ok | 1 | 0 | 165 X 12 | 920 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 78 X 13 | 960 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 960 | 2110 | 0 X 0 | 0 | 0 | 848.5 | 2046 | 37.5
85 |  | 1303 | BD01 | Left | 935 | 2100 | 175 | 175 | 3 | 1 | NA | -15 | 0 | 3 | 1 | 950 | 2100 | 165 | Correct Width to 950 | All Ok | 1 | 0 | 165 X 12 | 920 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 78 X 13 | 960 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 960 | 2110 | 0 X 0 | 0 | 0 | 848.5 | 2046 | 37.5
86 |  | 1304 | BD01 | Right | 940 | 2090 | 210 | 210 | 3 | 1 | NA | -10 | -10 | 3 | 1 | 950 | 2100 | 210 | Correct Width to 950 | Correct Heigt to 2100 | 1 | 0 | 210 X 12 | 920 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 960 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 960 | 2110 | 110 X 15 | 0 | 2090 | 848.5 | 2046 | 37.5
87 |  | 1304 | BD01 | Left | 945 | 2070 | 145 | 145 | 2 | 1 | NA | -5 | -30 | 2 | 1 | 950 | 2100 | 135 | Correct Width to 950 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 930 | 2090 | 115 X 44 | Telescopic | 35 | 35 X 48 X 13 | 970 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 970 | 2110 | 0 X 0 | 0 | 0 | 858.5 | 2046 | 37.5
88 |  | 1101 | T001 | Right | 800 | 2110 | 130 | 130 | 1 | 1 | NA | 0 | 10 | 1 | 1 | 800 | 2100 | 115 | All Ok | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
89 |  | 1101 | T001 | Right | 825 | 2120 | 130 | 130 | 2 | 2 | NA | 25 | 20 | 2 | 2 | 800 | 2100 | 115 | Correct Width to 800 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
90 |  | 1103 | T001 | Right | 805 | 2090 | 130 | 130 | 3 | 3 | NA | 5 | -10 | 3 | 3 | 800 | 2100 | 115 | Correct Width to 800 | Correct Heigt to 2100 | 1 | 1 | 110 X 12 | 770 | 2080 | 115 X 44 | Flat | 35 | 35 X 8 | 810 | 2105 | Telescopic | 35 | 35 X 28 X 13 | 810 | 2100 | 0 X 0 | 0 | 0 | 698.5 | 2036 | 37.5
91 |  | 1103 | T001 | Left | 800 | 2090 | 130 | 130 | 4 | 4 | NA | 0 | -10 | 4 | 4 | 800 | 2100 | 115 | All Ok | Correct Heigt to 2100 | 2 | 1 | 110 X 12 | 760 | 2080 | 115 X 44 | Flat | 35 | 35 X 8 | 800 | 2105 | Telescopic | 35 | 35 X 28 X 13 | 800 | 2100 | 0 X 0 | 0 | 0 | 688.5 | 2036 | 37.5
92 |  | 1103 | T001 | Right | 805 | 2100 | 130 | 130 | 5 | 5 | NA | 5 | 0 | 5 | 5 | 800 | 2100 | 115 | Correct Width to 800 | All Ok | 2 | 1 | 110 X 12 | 760 | 2080 | 115 X 44 | Flat | 35 | 35 X 8 | 800 | 2105 | Telescopic | 35 | 35 X 28 X 13 | 800 | 2100 | 0 X 0 | 0 | 0 | 688.5 | 2036 | 37.5
93 |  | 1104 | T001 | Left | 805 | 2100 | 130 | 130 | 6 | 1 | NA | 5 | 0 | 6 | 1 | 800 | 2100 | 115 | Correct Width to 800 | All Ok | 2 | 0 | 110 X 12 | 760 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 800 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 800 | 2110 | 0 X 0 | 0 | 0 | 688.5 | 2046 | 37.5
94 |  | 1104 | T001 | Left | 800 | 2110 | 130 | 130 | 7 | 1 | NA | 0 | 10 | 7 | 1 | 800 | 2100 | 115 | All Ok | Correct Heigt to 2100 | 2 | 0 | 110 X 12 | 760 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 800 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 800 | 2110 | 0 X 0 | 0 | 0 | 688.5 | 2046 | 37.5
95 |  | 1201 | T001 | Right | 810 | 2100 | 130 | 130 | 1 | 1 | NA | 10 | 0 | 1 | 1 | 800 | 2100 | 115 | Correct Width to 800 | All Ok | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
96 |  | 1201 | T001 | Right | 790 | 2100 | 130 | 130 | 1 | 1 | NA | -10 | 0 | 1 | 1 | 800 | 2100 | 115 | Correct Width to 800 | All Ok | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
97 |  | 1203 | T001 | Right | 805 | 2080 | 130 | 130 | 1 | 1 | NA | 5 | -20 | 1 | 1 | 800 | 2100 | 115 | Correct Width to 800 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
98 |  | 1203 | T001 | Left | 790 | 2085 | 130 | 130 | 1 | 1 | NA | -10 | -15 | 1 | 1 | 800 | 2100 | 115 | Correct Width to 800 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
99 |  | 1203 | T001 | Right | 810 | 2100 | 130 | 130 | 1 | 1 | NA | 10 | 0 | 1 | 1 | 800 | 2100 | 115 | Correct Width to 800 | All Ok | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
100 |  | 1204 | T001 | Left | 795 | 2110 | 130 | 130 | 1 | 1 | NA | -5 | 10 | 1 | 1 | 800 | 2100 | 115 | Correct Width to 800 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
101 |  | 1204 | T001 | Left | 790 | 2115 | 140 | 140 | 1 | 1 | NA | -10 | 15 | 1 | 1 | 800 | 2100 | 115 | Correct Width to 800 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
102 |  | 1301 | T001 | Right | 815 | 2100 | 130 | 130 | 1 | 1 | NA | 15 | 0 | 1 | 1 | 800 | 2100 | 115 | Correct Width to 800 | All Ok | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
103 |  | 1301 | T001 | Right | 795 | 2100 | 130 | 130 | 1 | 1 | NA | -5 | 0 | 1 | 1 | 800 | 2100 | 115 | Correct Width to 800 | All Ok | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
104 |  | 1303 | T001 | Right | 810 | 2100 | 130 | 130 | 1 | 1 | NA | 10 | 0 | 1 | 1 | 800 | 2100 | 115 | Correct Width to 800 | All Ok | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
105 |  | 1303 | T001 | Right | 790 | 2100 | 130 | 130 | 1 | 1 | NA | -10 | 0 | 1 | 1 | 800 | 2100 | 115 | Correct Width to 800 | All Ok | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
106 |  | 1303 | T001 | Left | 795 | 2110 | 130 | 130 | 1 | 1 | NA | -5 | 10 | 1 | 1 | 800 | 2100 | 115 | Correct Width to 800 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
107 |  | 1304 | T001 | Left | 800 | 2140 | 130 | 130 | 1 | 1 | NA | 0 | 40 | 1 | 1 | 800 | 2100 | 115 | All Ok | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
108 |  | 1304 | T001 | Left | 800 | 2140 | 130 | 130 | 1 | 1 | NA | 0 | 40 | 1 | 1 | 800 | 2100 | 115 | All Ok | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
109 |  | 1101 | T001 | Right | 815 | 2110 | 130 | 130 | 1 | 1 | NA | 15 | 10 | 1 | 1 | 800 | 2100 | 115 | Correct Width to 800 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
110 |  | 1101 | T001 | Right | 770 | 2110 | 140 | 140 | 1 | 1 | NA | -30 | 10 | 1 | 1 | 800 | 2100 | 115 | Correct Width to 800 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
111 |  | 1102 | T001 | Right | 775 | 2090 | 140 | 140 | 3 | 1 | NA | -25 | -10 | 3 | 1 | 800 | 2100 | 115 | Correct Width to 800 | Correct Heigt to 2100 | 1 | 0 | 110 X 12 | 770 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 810 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 810 | 2110 | 0 X 0 | 0 | 0 | 698.5 | 2046 | 37.5
112 |  | 1102 | T001 | Right | 820 | 2120 | 130 | 130 | 1 | 1 | NA | 20 | 20 | 1 | 1 | 800 | 2100 | 115 | Correct Width to 800 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
113 |  | 1103 | T001 | Right | 845 | 2100 | 130 | 130 | 1 | 1 | NA | 45 | 0 | 1 | 1 | 800 | 2100 | 115 | Correct Width to 800 | All Ok | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
114 |  | 1103 | T001 | Right | 810 | 2100 | 130 | 130 | 1 | 1 | NA | 10 | 0 | 1 | 1 | 800 | 2100 | 115 | Correct Width to 800 | All Ok | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
115 |  | 1103 | T001 | Left | 790 | 2100 | 130 | 130 | 1 | 1 | NA | -10 | 0 | 1 | 1 | 800 | 2100 | 115 | Correct Width to 800 | All Ok | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
116 |  | 1201 | T001 | Right | 820 | 2120 | 130 | 130 | 1 | 1 | NA | 20 | 20 | 1 | 1 | 800 | 2100 | 115 | Correct Width to 800 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
117 |  | 1201 | T001 | Right | 790 | 2120 | 130 | 130 | 1 | 1 | NA | -10 | 20 | 1 | 1 | 800 | 2100 | 115 | Correct Width to 800 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
118 |  | 1202 | T001 | Left | 755 | 2080 | 130 | 130 | 3 | 1 | NA | -45 | -20 | 3 | 1 | 800 | 2100 | 115 | Correct Width to 800 | Correct Heigt to 2100 | 1 | 0 | 110 X 12 | 770 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 810 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 810 | 2110 | 0 X 0 | 0 | 0 | 698.5 | 2046 | 37.5
119 |  | 1202 | T001 | Right | 780 | 2095 | 130 | 130 | 3 | 1 | NA | -20 | -5 | 3 | 1 | 800 | 2100 | 115 | Correct Width to 800 | Correct Heigt to 2100 | 1 | 0 | 110 X 12 | 770 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 810 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 810 | 2110 | 0 X 0 | 0 | 0 | 698.5 | 2046 | 37.5
120 |  | 1203 | T001 | Right | 795 | 2070 | 130 | 130 | 1 | 1 | NA | -5 | -30 | 1 | 1 | 800 | 2100 | 115 | Correct Width to 800 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
121 |  | 1203 | T001 | Left | 800 | 2080 | 130 | 130 | 1 | 1 | NA | 0 | -20 | 1 | 1 | 800 | 2100 | 115 | All Ok | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
122 |  | 1203 | T001 | Right | 810 | 2090 | 130 | 130 | 1 | 1 | NA | 10 | -10 | 1 | 1 | 800 | 2100 | 115 | Correct Width to 800 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
123 |  | 1301 | T001 | Right | 790 | 2115 | 130 | 130 | 1 | 1 | NA | -10 | 15 | 1 | 1 | 800 | 2100 | 115 | Correct Width to 800 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
124 |  | 1301 | T001 | Right | 775 | 2120 | 130 | 130 | 1 | 1 | NA | -25 | 20 | 1 | 1 | 800 | 2100 | 115 | Correct Width to 800 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
125 |  | 1303 | T001 | Right | 795 | 2090 | 130 | 130 | 1 | 1 | NA | -5 | -10 | 1 | 1 | 800 | 2100 | 115 | Correct Width to 800 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5
126 |  | 1303 | T001 | Right | 805 | 2110 | 130 | 130 | 1 | 1 | NA | 5 | 10 | 1 | 1 | 800 | 2100 | 115 | Correct Width to 800 | Correct Heigt to 2100 | 0 | 0 | 0 X 0 | 780 | 2090 | 115 X 44 | Flat | 35 | 35 X 8 | 820 | 2110 | Telescopic | 35 | 35 X 28 X 13 | 820 | 2110 | 0 X 0 | 0 | 0 | 708.5 | 2046 | 37.5